## Munka1
Name of area | Deck | Number ID of that area. | Cable trays in the area | Penetrations | Number of uncoordinated cables on the wall | Number of uncoordinated cables on the ceiling | How many thick cables terminates | How many thin cables terminates | How many thick cables are going trough that area? | How many cables from the total has already been pulled in that area. (that goes trough or stopps there) | How many penetrations do we have there | Current blocking points | Handover KW if no blocking
Misc. Room | Main | 1021 | 1E5101; 1E5103;1E5102; 1E5104; | 1EDH401;1EDH505;1EDH509;1EDH510
Refrigeration Cell | Main | 1010 | 1E6204; | 1EDH519;
Refrigeration Cell | Main | 1008 | 1E6205;
Refrigeration Cell | Main | 1006 | 1E6206 | 1EDH618;1EDH619;
Cabin area Main Deck | Main |  | 2E2111;2E2112;2E2113;1E3101;1E3102;1E3103;1E3104;1E3105;1E4101;1E4102;1E4103;1E4104;1E4105;1E4106;1E4107;1E4108;1E4109;1E4110;1E4110;1E4111;1E4112;1E4113;1E2204;1E2205;1E3201;1E3202;1E3203;1E3204;1E3205;1E4202;1E4203;1E4204;1E4205;1E4206;1E4207; 1E4208;1E4209;1E4210;1E4211;1E4212;1E4213 | 1EDH205;1EDV301;1EDH301;1EDH302;1EDV403;1EDV401;1EDH401;1EDH203;1EDH512; 1EDH502; 1EDH513; 1EDV614;1EDH519;1EDH518;1EDH517;1EDH403; 1EDH404;1EDH307;1EDH208;1EDH207;2EDV230;2EDV305;2EDV404; 2EDV405;2EDV502; 2EDV401; 2EDV402;2EDV407;2EDV506;
Corridor Main Deck | Main |  | 1E2002;1E2003;1E2004;1E3001;1E3002;1E3003;1E3004;1E3005;1E4002;1E4003;1E4004;1E4005;1E4006;1E4007;1E4008;1E4009;1E4010;1E4011;1E4012;1E4013;1E5002;1E5204;1E5205;1E5206;1E6001;1E6002;1E6003 | 1EDH217;1EDH201;1EDH303;1EDH402;1EDV404;2EDV230;2EDV305;1EDH504;1EDV614;1EDH516
Double bottom Sp. 18–30 | Main |  | 0E2201;0E2202;0E2203;0E2101;0E2102;0E2103 | 0EDH201;
MKR (Ship-to-Ship) | Middle | 2063 | 2E2105; 2E2103;2E2100;2E2113;2E2112;2E2110;2E2106;2E2107; | 2EDV203;2EDV204;2EDV205;2EDV206;2EDV207;2EDV208;2EDV209;2EDV201;2EDH201;2EDH202;2EDH204;2EDH205;2EDH203;3EDV210;3EDV211;3EDV215;3EDV204
Backoffice | Middle | 2045 | 2E4002;2E4102;2E4101;2E4003;2E4103; | 2EDV401;2EDV402;2EDH402;2EDH304;2EDH305;2EDV406;2EDH401;
Atrium Upper | Upper |  | 3E4102;3E4102;3E4104;3E4105;3E4106;3E4107;3E4109;3E4110;3E4111;3E4112;3E4113;3E4007;3E4201;3E4001;3E4202;3E4203;3E4002;3E4204;3E4205;3E4206;3E4208;3E4209;3E4006;3E4211;3E4210; | 3EDH302;3EDH304;3EDV402;3EDH402;3EDH414;3EDV408;3EDH406;3EDV405;3EDH407;3EDV406;3EDV403;3EDH412;3EDH405;3EDH303;3EDV401;3EDH301;3EDH401;3EDH413;3EDV409;3EDV410;3EDH403;3EDV404;3EDH408;3EDH409;3EDH411;3EDV407;3EDH410;4EDV401;4EDV402;4EDV403;4EDV407
Atrium middle | Middle |  | 2E4001;2E4004;2E4201;2E4006;2E4105;2E4208;2E4202;2E4207;2E4209;2E4106;2E4107;2E4108;2E4109;2E4113;2E4110;2S4002;2E4215;2E4214;2S4001;2E4213;2E4212;2E4211;2E4210; 2E4209;2E4005; | 3EDV408;3EDV405;3EDV406;3EDV403;3EDV407;3EDV404;3EDV410;3EDV401;2EDH306;2EDH412;2EDH413;2EDH414;2EDH415;2EDV408;2EDV505;2EDH410;2EDH409;2EDH411;2EDV412;2EDH420;2EDH408;2EDH407;2EDH406;2EDH405;2EDH404
Restaurant | Middle | 2020 | 2E5201;2E5101;2E5202;2E5102;2E5203;2E5204;2E5205;2E5105;2E5106;2E5206;2E5207;2E5107;2E5208;2E5211;2S5101;2S5001;2S5102;2E5103;2S5103;2S5104;2E5104;2S5105;2S5106;2S5107;2S5108;2E5108;2E5110;2E5109; | 2EDV502;2EDV505;2EDH410;2EDH409;2EDV501;2EDH411;2EDV506;2EDV504;2EDH501;2EDH502;2EDV517;2EDV508;2EDH503;3EDV505;3EDV513;3EDV512;3EDV509;3EDV507;3EDV510;3EDV503;3EDV504;3EDV502;3EDV506;3EDV501;3EDV403;3EDV406;3EDV405;3EDV404;
Galley | Middle | 2010 | 2e6202;2E6200;2E6000;2E6001;2E6101;2E6002;2E6003;2E6102;2E6200;2E6201;2E6203;2E6204; | 2EDH503;2EDH502;2EDH501;2EDH610;2EDH601;2EDH602;2EDH603;2EDV605;2EDV608;2EDV603;2EDV606;2EDV607;2EDV609;3EDV601;3EDV602;
Winches | Middle | 2004, 2007 | 2E6208;2E6099;2E6107; | 2EDH606;2EDH605;2EDH609
Cabins MiD | Middle
Corridor MiD | Middle |  | 2E2001;2E2002;2E2003;2E2004;2E2005;2E2006;2E2007;2E2008;2E2009;2E3001;2E3002;2E3003;2E3004;2E3005;2E3006;2E3007;2E3008;2E3009;2E3010;2E3011; | 2EDH207;2EDH212;2EDH208;2EDV230;2EDH211;2EDV305;2EDH317;2EDH312;2EDH314;2EDH306;3EDV203;3EDV205;3EDV206;3EDV214;3EDV213;
AC 3–5 | Upper | 3050 | 3E4209;3E4006;3E4111; | 3EDH404;3EDH403;3EDV410;3EDV409;
Winter Garden | Upper | 3020.301 | 3E5208;3E5001;3E5109
Lounge | Upper | 3030 | 3E5100;3E5101;3E5102;3E5103;3E5104;3E5105;3E51006;3E5107;3E5108;3E5200;3E5201;3E5202;3E5203;3E5204;3E5205;3E5206;3E5207;3E5000; | 3EDH411;3EDH410;3EDV407;3EDH405;3EDV501;3EDV502;3EDV506;3EDV504;3EDV503;3EDV510;3EDV507;3EDV505;3EDV512;3EDV513;3EDV509;
Cabins UpD | Upper |  | 3E2101;3E2102;3E2103;3E2104;3E2105;3E2106;3E2107;3E2111;3E2112;3E3101;3E3102;3E3103;3E3104;3E3105;3E3106;3E3107;3E3108;3E3109;3E3110;3E31111;3E3112; | 3EDH206;3EDH211;3EDH304;3EDH302;3EDV212;3EDV205;3EDV206;3EDV214;3EDV213;
Corridor UpD | Upper |  | 3E2002;3E2003;3E2004;3E2005;3E2006;3E2007;3E2008;3E2012;3E2013;3E3001;3E3002;3E3003;3E3004;3E3005;3E3006;3E3007;3E3008;3E3009;3E3010;3E3011;3E3012;3E3013; | 3EDH205;3EDH210;3EDH301;